## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-11-10 |  |  |  |  | November | [20 empty] | December
Scrolling Increment: | 1 | time axis 2022-11-11 to 2023-01-05
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-11-11 to 2023-01-05
TITLE 1
Task 1 | Goal | Name | 25% | 2022-11-10 | 3 | 2022-11-11: 2; 2022-11-12: 2
Task 2 | Milestone |  |  | 2022-11-15 | 1 | bar: 2022-11-15
Task 3 | Low Risk |  | 50% | 2022-11-07 | 10
Task 4 | Milestone |  |  | 2022-11-30 | 1 | bar: 2022-11-30
Task 5 | Med Risk |  | 10% | 2022-11-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-11-16 | 13
Task 2 | On Track |  | 50% | 2022-11-18 | 9
Task 3 | Low Risk |  | 33% | 2022-11-23 | 11
Task 4 | Milestone |  |  | 2022-11-25 | 1 | bar: 2022-11-25
Task 5 |  |  |  | 2022-11-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-11-25 | 4
Task 2 | Med Risk |  |  | 2022-11-28 | 14
Task 3 | On Track |  |  | 2022-12-13 | 6
Task 4 | Goal |  |  | 2022-12-17 | 3 | 2022-12-17: 2; 2022-12-18: 2; 2022-12-19: 2
Task 5 | Low Risk |  |  | 2022-11-16 | 19
TITLE 4
Task 1 |  |  |  | 2022-12-20 | 15
Task 2 |  |  |  | 2023-01-03 | 5
Task 3 | Milestone |  |  | 2023-02-14 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
Nsafe
[5 empty] | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
KATUMBIRE BOB BELLS
Project Start Date: | 2022-10-01 |  |  |  |  | October | [34 empty] | November
Scrolling Increment: | 0 | time axis 2022-10-01 to 2022-11-25
Milestone description | Category | Assigned to | Progress | Start | Days | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
IDEATION
WRITE UP | Goal | BOB BELLS | 100% | 2022-10-01 | 3 | S: 2; S: 2; M: 2
PROBLEM STATEMENT | Milestone | BOB BELLS | 100% | 2022-10-04 | 1 | bar: T
RESEARCH
PROJECT SCOPE | On Track | BOB BELLS | 90% | 2022-10-09 | 5
USER RESEARCH | On Track | BOB BELLS | 79% | 2022-10-11 | 6
GATHER REQUIREMENTS | On Track | BOB BELLS | 85% | 2022-10-11 | 11
KICK OFF | Milestone | BOB BELLS | 100% | 2022-10-23 | 1 | bar: S
DESIGN
SKETCKING | On Track | BOB BELLS | 90% | 2022-10-25 | 4
FLOW CHARTS | Med Risk | BOB BELLS | 100% | 2022-10-28 | 7
PROTOTYPING | On Track | BOB BELLS | 83% | 2022-11-04 | 6
IMPLEMENTATION
LEARNING PYTHON | On Track | BOB BELLS | 5% | 2022-11-08 | 15
SCRIPTING (terminal based) | On Track | BOB BELLS |  | 2022-11-18 | 10
TESTING | Milestone | BOB BELLS |  | 2022-11-27 | 1
G.U.I implementation | High Risk | BOB BELLS |  | 2022-11-28 | 10
TESTING | Goal | BOB BELLS |  | 2022-12-07 | 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2022-11-10 |  |  |  |  | November | [20 empty] | December | [27 empty] | January
Scrolling Increment: | 5 | time axis 2022-11-15 to 2023-01-09
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2022-11-15 to 2023-01-09
TITLE 1
Task 1 | Goal | Name | 25% | 2022-11-10 | 3
Task 2 | Milestone |  |  | 2022-11-15 | 1 | bar: 2022-11-15
Task 3 | Low Risk |  | 50% | 2022-11-07 | 10
Task 4 | Milestone |  |  | 2022-11-30 | 1 | bar: 2022-11-30
Task 5 | Med Risk |  | 10% | 2022-11-16 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2022-11-16 | 13
Task 2 | On Track |  | 50% | 2022-11-18 | 9
Task 3 | Low Risk |  | 33% | 2022-11-23 | 11
Task 4 | Milestone |  |  | 2022-11-25 | 1 | bar: 2022-11-25
Task 5 |  |  |  | 2022-11-26 | 24
TITLE 3
Task 1 | On Track |  |  | 2022-11-25 | 4
Task 2 | Med Risk |  |  | 2022-11-28 | 14
Task 3 | On Track |  |  | 2022-12-13 | 6
Task 4 | Goal |  |  | 2022-12-17 | 3 | 2022-12-17: 2; 2022-12-18: 2; 2022-12-19: 2
Task 5 | Low Risk |  |  | 2022-11-16 | 19
TITLE 4
Task 1 |  |  |  | 2022-12-20 | 15
Task 2 |  |  |  | 2023-01-03 | 5
Task 3 | Milestone |  |  | 2023-02-14 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one